## Actor-Usecase
USECASE POINT ESTIMATION
Project Code | SP22SE11 |  |  | Supervisor | Phạm Công Thành
Project Name | Management of gas stove production |  |  | Customer
I. Summary
Unadjusted Actor Weight (UAW) |  |  | 16 | Total UCP | 421.7335
Unadjusted Use-Case Weight (UUCW) |  |  | 415 | Estinmation Effort (manhour) | 8434.67
Technical Complexity Factor (TCF) |  |  | 1.03 | Number of Member | 4
Environmental Complexity Factor (ECF) |  |  | 0.95 | Average Effort for each member | 2108.6675
I. Actor List
Unadjusted Actor Weight (UAW) |  |  | 16
No | Actor Name | Difficulty | Weight | Type | Description
1 | Unauthenticated User | Simple | 1 | Human
2 | Customer | Simple | 1 | Human
3 | Employee | Average | 2 | Human
4 | Worker | Simple | 1 | Human
5 | Order Department | Average | 2 | Human
6 | Manufacturing Department | Complex | 3 | Human
7 | Section Department | Complex | 3 | Human
8 | Admin | Complex | 3 | Human
9 |  |  | 0
10 |  |  | 0
II. Usecase List
Unadjusted Use-Case Weight (UUCW) |  |  | 415
No | Actor | UC Name | Difficulty | Priority | Weight | Description
1 | Unauthenticated User | Login with Google | Simple |  | 5
2 | Unauthenticated User | View product list | Simple |  | 5
3 | Unauthenticated User | View product detail | Simple |  | 5
4 | Customer | View profile | Simple |  | 5
5 | Customer | Update profile | Simple |  | 5
6 | Customer | Make orders | Average |  | 10
7 | Customer | Log out | Simple |  | 5
8 | Employee | Update password | Simple |  | 5
9 | Employee | Get notification list | Simple |  | 5
10 | Employee | Get notification details | Simple |  | 5
11 | Employee | Log out | Simple |  | 5
12 | Worker | View attendance list | Simple |  | 5
13 | Order department | Manage order | Simple |  | 5
14 | Order department | Update order | Average |  | 10
15 | Order department | Get order list | Simple |  | 5
16 | Order department | Get order's information | Simple |  | 5
17 | Order department | Create order | Average |  | 10
18 | Manufacturing department | Alert deadlines | Average |  | 10 | Include: Push notification
19 | Manufacturing department | Get section list | Simple |  | 5
20 | Manufacturing department | View section's details | Simple |  | 5
21 | Manufacturing department | View order report | Simple |  | 5
22 | Manufacturing department | Manage process | Simple |  | 5
23 | Manufacturing department | Update process | Average |  | 10
24 | Manufacturing department | Create process | Average |  | 10
25 | Manufacturing department | Add section to process | Simple |  | 5
26 | Manufacturing department | Get order list | Simple |  | 5
27 | Manufacturing department | Get order's information | Simple |  | 5
28 | Section department | View attendance report | Simple |  | 5
29 | Section department | Manage material | Simple |  | 5
30 | Section department | Send material request | Average |  | 10 | Include: Push notification
31 | Section department | Get material list | Simple |  | 5
32 | Section department | Get material details | Simple |  | 5
33 | Section department | Create material | Average |  | 10
34 | Section department | Manage daily report | Simple |  | 5
35 | Section department | Create daily report | Average |  | 10
36 | Section department | View daily report | Simple |  | 5
37 | Section department | Send daily report | Simple |  | 5
38 | Admin | Manage account | Simple |  | 5
39 | Admin | Create account | Average |  | 10
40 | Admin | Update account | Average |  | 10
41 | Admin | Get account list | Simple |  | 5
44 | Admin | Get account details | Simple |  | 5
45 | Admin | Disable account | Simple |  | 5
46 | Admin | Manage material | Simple |  | 5
47 | Admin | Create material | Average |  | 10
48 | Admin | Update material | Average |  | 10
49 | Admin | Get material list | Simple |  | 5
50 | Admin | Get material details | Simple |  | 5
51 | Admin | Disable material | Simple |  | 5
52 | Admin | Manage material request | Simple |  | 5
53 | Admin | View material request list | Simple |  | 5
54 | Admin | View request details | Simple |  | 5
55 | Admin | Accept request | Average |  | 10 | Include: Push notification
56 | Admin | Deny request | Average |  | 10 | Include: Push notification
57 | Admin | Manage product | Simple |  | 5
58 | Admin | Create product | Average |  | 10
59 | Admin | Update product | Average |  | 10
60 | Admin | Get product list | Simple |  | 5
61 | Admin | Get product details | Simple |  | 5
62 | Admin | Disable product | Simple |  | 5
63 | Admin | Manage section's worker account | Simple |  | 5
64 | Admin | Add worker's account | Simple |  | 5
65 | Admin | Remove worker's account | Simple |  | 5
66 | Admin | Import attendance file | Complex |  | 15
67 |  |  |  |  | 0
68 |  |  |  |  | 0
69 |  |  |  |  | 0
70 |  |  |  |  | 0
71 |  |  |  |  | 0
72 |  |  |  |  | 0
73 |  |  |  |  | 0
74 |  |  |  |  | 0
75 |  |  |  |  | 0
76 |  |  |  |  | 0
77 |  |  |  |  | 0
78 |  |  |  |  | 0
79 |  |  |  |  | 0
80 |  |  |  |  | 0
Note on E26: ====== ID#AAAAQtOG3FI Admin (2021-10-11 12:24:52) More detail in references sheet

## UCP Estimate
Technical Factor | Weight | Relevance 0-5 | Score
T1 Distributed System | 2 | 5 | 10
T2 Performance | 1 | 3 | 3
T3 End User Efficiency | 1 | 4 | 4
T4 Complex Internal Processing | 1 | 3 | 3
T5 Reusability | 1 | 4 | 4
T6 Easy to Install | 0.5 | 2 | 1
T7 Easy to Use | 0.5 | 4 | 2
T8 Portability | 2 | 2 | 4
T9 Easy to Change | 1 | 2 | 2
T10 Concurrency | 1 | 3 | 3
T11 Special Security Features | 1 | 3 | 3
T12 Provides Direct Access for Third Parties | 1 | 2 | 2
T13 Special User Training Facilities Are Required | 1 | 2 | 2
Sum |  |  | 43
Complexity Factor |  |  | 0.6
C2 |  |  | 0.01
TCF |  |  | 1.03
Environmental Factor | Weight | Impacte 0-5 | Score
E1 Familiarity With UML | 1.5 | 4 | 6
E2 Part-Time Workers | -1 | 3 | -3
E3 Analyst Capability | 0.5 | 3 | 1.5
E4 Application Experience | 0.5 | 3 | 1.5
E5 Object-Oriented Experience | 1 | 3 | 3
E6 Motivation | 1 | 4 | 4
E7 Difficult Programming Language | -1 | 4 | -4
E8 Stable Requirements | 2 | 3 | 6
Sum (ETF) |  |  | 15
ECF = 1.4 +(-0.03 * Environmental Total Factor) |  |  | 0.95
PF (Historical based average man hours per use case point) |  |  | 20
Estimation Usecase Point (UCP = UUCP * TCF * ECF) |  | 421.7335
Estimation Effort (manhours) |  | 8434.67

## References
I. Actor
No | Difficulty | Multiplier | Description
1 | Simple | 1 | Simple actors are other systems that communicate with your software via a pre-defined API. An API could be exposed through a dll, or as a REST, SOAP, or any web-service API or remote procedure call (RPC). The key element is that you are exposing interaction with your software through a specific, well-defined mechanism.
2 | Average | 2 | Average actors can either be human beings interacting in a well defined protocol, or they could be systems that interact through a more complex or flexible API.
3 | Complex | 3 | The original definition of complex actors specifies that users who interact with the software through a graphical user interface are complex actors. While that is true, the same classifcation should apply to users who interact with the system in unpredictable ways. An AJAX interface that exposes more of the underlying application (and data stores) than would be available through a rigid protocol might introduce similar complexity.
II. Usecase
No | Difficulty | Multiplier | Description
1 | Simple | 5 | Simple Use Case - up to 3 transactions.
2 | Average | 10 | Average Use Case - 4 to 7 transactions.
3 | Complex | 15 | Complex Use Case - more than 7 transactions.
III. MoSCoW Prioritisation
No | Rules | Priority | Description
1 | Must Have | High | Requirements labelled as Must have are critical to the current delivery timebox in order for it to be a success. If even one Must have requirement is not included, the project delivery should be considered a failure
2 | Should Have | Medium | Requirements labelled as Should have are important but not necessary for delivery in the current delivery timebox.
3 | Could Have | Low | Requirements labelled as Could have are desirable but not necessary and could improve the user experience or customer satisfaction for a little development cost.
4 | Won’t Have this time | Very Low | Requirements labelled as Won't have, have been agreed by stakeholders as the least-critical, lowest-payback items, or not appropriate at that time.